## Tasks
Autism-friendly_app
COMPLETE
Task ID | Task Name | Assignee | Due Date | Priority | Status | Comment Count
86cynwp44 | ‎Define project goals and features | Vishvadharshini .A, Ashwin B 22MIS1194, yazhini.g2022@vitstudent.ac.in | 2025-01-06 | HIGH | COMPLETE | 1
86cypf32n | Research autism-friendly UX/UI design | Ashwin B 22MIS1194 | 2025-01-10 | NORMAL | COMPLETE | 1
86cypf357 | Create wireframes for app modules | Ashwin B 22MIS1194, yazhini.g2022@vitstudent.ac.in | 2025-01-12 | HIGH | COMPLETE | 0
86cypf3vg | Set up ClickUp and team workflow | Vishvadharshini .A | 2025-01-05 | NORMAL | COMPLETE | 0
86cypf3yc | Design conversation flow templates | yazhini.g2022@vitstudent.ac.in | 2025-01-17 | HIGH | COMPLETE | 0
86cypf410 | Create chatbot scripts for common social scenarios | Ashwin B 22MIS1194, Vishvadharshini .A | 2025-01-20 | HIGH | COMPLETE | 0
86cypf43c | Implement speech/text input features | Vishvadharshini .A | 2025-01-22 | NORMAL | COMPLETE | 0
86cypf44q | Add real-time feedback mechanism | yazhini.g2022@vitstudent.ac.in | 2025-01-25 | NORMAL | COMPLETE | 0
86cypf4a6 | Design emotion-based quizzes | Ashwin B 22MIS1194, yazhini.g2022@vitstudent.ac.in | 2025-02-02 | LOW | COMPLETE | 1
86cypf4b8 | Plan customizable daily routine templates | Vishvadharshini .A | 2025-02-10 | NORMAL | COMPLETE | 0
86cypf4cy | Design routine tracking UI | yazhini.g2022@vitstudent.ac.in | 2025-02-15 | NORMAL | COMPLETE | 0
86cypf4ew | Train chatbot with adaptive learning | Vishvadharshini .A, yazhini.g2022@vitstudent.ac.in | 2025-03-05 | HIGH | COMPLETE | 0
86cypf4gf | Integrate ML to personalize communication practice | Ashwin B 22MIS1194, Vishvadharshini .A | 2025-03-10 | HIGH | COMPLETE | 0
86cypf4kq | Test and fine-tune chatbot responses | yazhini.g2022@vitstudent.ac.in | 2025-03-12 | NORMAL | COMPLETE | 0
86cypf4p1 | Create educational videos on social skills | yazhini.g2022@vitstudent.ac.in, Ashwin B 22MIS1194 | 2025-03-18 | NORMAL | COMPLETE | 1
86cypf4u5 | Review and upload content into app | Vishvadharshini .A | 2025-03-25 | HIGH | COMPLETE | 0
86cypf4ww | Internal testing of each module | Ashwin B 22MIS1194, yazhini.g2022@vitstudent.ac.in | 2025-03-30 | URGENT | COMPLETE | 0
86cypf4za | Gather peer/user feedback | yazhini.g2022@vitstudent.ac.in | 2025-04-01 | NORMAL | COMPLETE | 0
86cypf517 | Bug fixes and refinements | Ashwin B 22MIS1194 | 2025-04-05 | URGENT | COMPLETE | 0
86cypf531 | Final polishing | Vishvadharshini .A, Ashwin B 22MIS1194, yazhini.g2022@vitstudent.ac.in | 2025-04-07 | URGENT | COMPLETE | 0
86cypf549 | Final review and checklist | yazhini.g2022@vitstudent.ac.in | 2025-04-07 | URGENT | COMPLETE | 0
86cypf55q | Submit final project | yazhini.g2022@vitstudent.ac.in, Vishvadharshini .A, Ashwin B 22MIS1194 | 2025-04-11 | HIGH | COMPLETE | 1